## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Lamontra Peters |  |  | PROJECT ID: | Oxygen Thieves (OT) - 001
PROJECT SPONSOR: | James Chrisman |  |  | PROJECT TITLE: | Thompson Project
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | Source | Assigned To | DELIVERABLES | STATUS / DATE | VALIDATION
REQ-001 | Mandatory | The system will create user accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT. | Should have | Medium
REQ-002 | Mandatory | The system will edit user accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT. | Nice to have | Low
REQ-003 | Mandatory | The system will delete user accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-004 | Mandatory | The system will create admin accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-005 | Mandatory | The system will edit admin accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-006 | Mandatory | The system will delete admin accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-007 | Mandatory | The system will create volunteer accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-008 | Mandatory | The system will edit volunteer accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-009 | Mandatory | The system will delete volunteer accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-010 | Mandatory | The system will allow account log-ins. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-011 | Mandatory | The system will grant user privileges based on account type. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed- 10/21/22 | Unit test and UAT.
REQ-012 | Should Have | The system will create news. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-013 | Should Have | The system will edit news. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-014 | Should Have | The system will delete news. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-015 | Should Have | The system will create announcements. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-016 | Should Have | The system will edit announcements. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-017 | Should Have | The system will delete announcements. | Medium | Service Desk | Larry Nguyen | Events | Completed- 10/21/22 | Unit test and UAT.
REQ-018 | Mandatory | The system will create grant proposals. | High | Service Desk | N/A | N/A | Not needed | Unit test and UAT.
REQ-019 | Mandatory | The system will edit grant proposals. | High | Service Desk | N/A | N/A | Not needed | Unit test and UAT.
REQ-020 | Mandatory | The system will delete grant proposals. | High | Service Desk | N/A | N/A | Not needed | Unit test and UAT.
REQ-021 | Should Have | The system will create events. | Medium | Service Desk | Larry Nguyen | Events | Completed - 10/21/22 | Unit test and UAT.
REQ-022 | Should Have | The system will edit events. | Medium | Service Desk | Larry Nguyen | Events | Completed - 10/21/22 | Unit test and UAT.
REQ-023 | Should Have | The system will delete events. | Medium | Service Desk | Larry Nguyen | Events | Completed - 10/21/22 | Unit test and UAT.
REQ-024 | Mandatory | The system will allow users to donate using the donation page. | High | Service Desk | Lamontra Peters | Donation Button | Completed - 10/21/22 | Unit test and UAT.
REQ-025 | Mandatory | The system will allow users to donate monthly through the subscription page. | High | Service Desk | Lamontra Peters | Donation Button | Completed - 10/21/22 | Unit test and UAT.
REQ-026 | Mandatory | The system will provide a log in page for created accounts. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed - 10/21/22 | Unit test and UAT.
REQ-027 | Nice to Have | The system will provide a search bar. | Low | Service Desk | Lamontra Peters | Home Page | Not needed | Unit test and UAT.
REQ-028 | Mandatory | The system will edit payments. | High | Service Desk | Lamontra Peters | Donation Button | Completed - 10/18/22 | Unit test and UAT.
REQ-029 | Mandatory | The system will delete payments. | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-030 | Nice to Have | The system will add testimonials. | Low | Service Desk | Parker Evans | About Us | Completed - 10/21/22 | Unit test and UAT.
REQ-031 | Nice to Have | The system will edit testimonials. | Low | Service Desk | Parker Evans | About Us | Completed - 10/21/22 | Unit test and UAT.
REQ-032 | Nice to Have | The system will delete testimonials. | Low | Service Desk | Parker Evans | About Us | Completed - 10/21/22 | Unit test and UAT.
REQ-033 | Should Have | The system will add resources for juveniles. | Medium | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-034 | Should Have | The system will edit resources for juveniles. | Medium | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-035 | Should Have | The system will allow resources to be deleted. | Medium | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-036 | Nice to Have | The system will add pictures to the carousel. | Low | Service Desk | Parker Evans | All | Completed-10/21/22 | Unit test and UAT.
REQ-037 | Nice to Have | The system will allow editing of photos in the carousel. | Low | Service Desk | Parker Evans | All | Completed-10/21/22 | Unit test and UAT.
REQ-038 | Nice to Have | The system will allow photos to be deleted from the carousel. | Low | Service Desk | Parker Evans | All | Completed-10/21/22 | Unit test and UAT.
REQ-039 | Mandatory | The system will allow organization accounts to be added. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed-10/21/22 | Unit test and UAT.
REQ-040 | Mandatory | The system will allow organization accounts to be edited. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed-10/21/22 | Unit test and UAT.
REQ-041 | Mandatory | The system will allow organization accounts to be deleted. | High | Service Desk | Larry Nguyen | Log In/ Sign up | Completed-10/21/22 | Unit test and UAT.
REQ-042 | Mandatory | The system will allow contact information to be added. | High | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-043 | Mandatory | The system will allow contact information to be edited. | High | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-044 | Mandatory | The system will allow contact information to be deleted. | High | Service Desk | Tarik Hemrekovic | Contact us | Completed-10/19/22 | Unit test and UAT.
REQ-045 | Nice to Have | The system will create attendees for events. | Low | Service Desk | Larry Nguyen | Volunteer | Completed-10/21/22 | Unit test and UAT.
REQ-046 | Nice to Have | The system will edit attendees. | Low | Service Desk | Larry Nguyen | Volunteer | Completed-10/21/22 | Unit test and UAT.
REQ-047 | Nice to Have | The system will delete attendees. | Low | Service Desk | Larry Nguyen | Volunteer | Completed-10/21/22 | Unit test and UAT.
REQ-048 | Mandatory | The system will conduct backups. | High | Service Desk | Ryan Foster | WordPress | Completed- 9/27/22 | Unit test and UAT.
REQ-049 | Mandatory | The system will be capable of recovery. | High | Service Desk | Ryan Foster | WordPress | Completed- 9/27/22 | Unit test and UAT.
REQ-050 | Mandatory | The system will create physical donations | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-051 | Mandatory | The system will edit physical donations | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-052 | Mandatory | The system will delete physical donations | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-053 | Mandatory | The system will create a donors list | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-054 | Mandatory | The system will edit a donors list | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-055 | Mandatory | The system will delete a donors list | High | Service Desk | Lamontra Peters | Donation Button | Completed-10/18/22 | Unit test and UAT.
REQ-056 | Mandatory | The system will create a volunteer list | High | Service Desk | Larry Nguyen | Volunteer | Completed 12/1/22 | Unit test and UAT.
REQ-057 | Mandatory | The system will edit a volunteer list | High | Service Desk | Larry Nguyen | Volunteer | Completed 12/1/22 | Unit test and UAT.
REQ-058 | Mandatory | The system will delete a volunteer list | High | Service Desk | Larry Nguyen | Volunteer | Completed 12/1/22 | Unit test and UAT.
REQ-059 | Mandatory | The system will create an about us page | Medium | Service Desk | Parker Evans | About Us | Completed-10/21/22 | Unit test and UAT.
REQ-060 | Mandatory | The system will allow editing of about us page | Medium | Service Desk | Parker Evans | About Us | Completed-10/21/22 | Unit test and UAT.
REQ-061 | Mandatory | The system will allow deletion of about us page | Medium | Service Desk | Parker Evans | About Us | Completed-10/21/22 | Unit test and UAT.
REQ-062 | N/A | The system will be designed and implemented with WordPress. |  |  |  |  | N/A | Unit test and UAT.
REQ-063 | N/A | The system will include a MySQL server for database management. |  |  |  |  | N/A | Unit test and UAT.
REQ-064 | N/A | The system will use IBM Cloud for storage and backups. |  |  |  |  | N/A | Unit test and UAT.
REQ-065 | N/A | The system will be user-friendly by providing a simple navigation experience and a satisfactory balance between text and images. |  |  |  |  | Completed 12/1/22 | Unit test and UAT.
REQ-066 | N/A | The system will provide the admin with volunteer, donation, and event information for easy scheduling. |  |  |  |  | Completed 12/1/22 | Unit test and UAT.
REQ-067 | N/A | The systems will be online and accessible at all times, unless maintenance requires the system to be temporarily offline. |  |  |  |  | Completed 12/1/22 | Unit test and UAT.
REQ-068 | N/A | The system will be accessible on desktop and most mobile browsers. |  |  |  |  | Completed 12/1/22 | Unit test and UAT.
CHANGE REQUESTS
CR-001 | Mandatory | Volunteer form needed for sign up | High | Service Desk | Ryan Foster | Sign Up | Completed 12/1/22 | Unit test and UAT.
CR-002 | Mandatory | Donation Form needs to cover entire page. Too small currently. | High | Service Desk | Lamontra Peters | Donation Button | Completed 12/1/22 | Unit test and UAT.
CR-003 | Mandatory | Volunteer background check must be implemented, | High | Service Desk | Ryan Foster | Sign Up | Not needed | Unit test and UAT.
CR-004 | Mandatory | Search bar must be implemented. | High | Service Desk | Larry Nguyen | Search Bar | Not needed | Unit test and UAT.

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Supplier - On projects with multiple suppliers you may want to add a field to note the supplier responsible.
WBS ID - Add WBS ID so that the requirement can be linked to the Work Breakdown Structure and project schedule.
Test case ID - Later in the project you may want to link the requirement to the test cases that will be used to
check that the requirement meets the business objective.
This template was provided by
https://www.stakeholdermap.com/